**Project Status Report I**

|  |
| --- |
| Date of Report Issue/Prepared: February 2, 2019 |

Report Prepared By: Chris Santin

Employer/Organization: George Brown/JC Consulting

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | JC Consulting Site | |
| 24 | |
| Start Date: **Jan 19, 2019** | End Date: **Feb 1, 2019** |
| Green | |

|  |
| --- |
| **Project Status Summary** |
| As the company expanding in both scale and technologies, they need to create a website to take data from users, analyze those data and produce values that can be used by employers to help them narrow down the potential and best fit candidates for any available positions. It acts like a bridge between job-seekers and employers and facilitates the processes of employment. The web app will allow:   * Job-seekers and hiring managers to set up accounts. * Interaction between users and employers (possibly emails, phone…) * Algorithms and logics behind the scene to analyze the data users input in and results in lists of potential workers who would be best fit for the jobs * Users could find lists of jobs that fit their levels of knowledge and skills * Employers could use the information that the core generates to accelerate the employing processes * Flags will be used to indicate jobs are currently available or whether users are interested in the jobs |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| Finish all documents in sprint 1, 2, 3, 4, 5 and mockup design | Build back-end environment |
| Completed design and initial creation of back end database and login/register systems | Develop front-end and UI |

Upcoming Objectives for Jan 19, 2019 to Feb 1, 2019

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | | **Planned Activities/Tasks for Next Period** | |  |
| Activity/Task | Assigned To | | Duration | Date |
| Continue building model/server for system | Hao | | 2 weeks | Feb 15th, 2019 |
| Finish a homepage and related pages (About, Contact, etc) | Quan + Tam | | 2 weeks | Feb 15th, 2019 |
| CRUD and base pages for candidate and consulting profiles | Chris + Tam | | 2 weeks | Feb 15th, 2019 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Milestones for Next Period** | | |
| Milestone (Objective) | | Assigned To | Delivery Date |
| Finish models and server for system | | Hao | Feb 15th, 2019 |
| Home, Candidate, and JC pages finished base design | | Quan, Chris + Tam | Feb 15th, 2019 |
| Complete CRUD for candidate and JC profiles | | Chris + Tam | Feb 15th, 2019 |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Lack of meetings with the Prof. Tyler and BA team. | Continue with already approved work and assumptions and submit finished working copy | Feb 28th, 2019 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| Difficulty for setting up meetings with Prof. Tyler and BA team.  Lack of feedbacks from stakeholder.  Group members cannot meet usually.  Collaborating between 2 groups (another group work on JC Consulting Company) | Hi  Hi  Low  Med | Hi  Hi  Low  Med | Continue working based on a few previous meetings with Tyler and company requirements  Design the template based on a team’s so far approved view.  Have regular weekly meetings, online contact, work at home.  Discuss through email and regular weekly in person meetings. |

**NOTE: Attach additional sheets if insufficient space available**